6. 	Actions from 19th Meeting

The actions are divided into those relating to the European data requirements and to those relating to North American data requirements. The numbering of the actions is the numbering of the relevant section in the respective data requirement documents. There are in addition some actions not directly related to the requirements lists and these are labelled as miscellaneous under section 6.3 below.  Additional points for information are included under section 6.4.

6.1	Actions related to European requirements

E.1.2.2 ATOVS level 1B data

Ask NESDIS to consult NWP Centres about the contention between NOAA-16 and 18 ATOVS processing. Recommendation: Provide NOAA-18 data in delayed mode for cal/val not to interfere with NOAA 16 operations. Switch to NOAA-18 can be made once NWP centres are satisfied with the data quality.

# Action: NESDIS, all NWP centres

METO: This has all been sorted out.

ECMWF: All issues solved

Met Office:

CLOSED

WMO will provide parties with the latest status of requirements and the appropriate references.

Action: WMO

Additionally, parties were notified that when the move to NSOF takes place, the early delivery of NOAA blind orbits will be supported provided the availability of the EUMETSAT ground segment.  NOAA-14 data to cease later this year when NESDIS moves to NSOF.

## E.1.3 Ozone retrieved profiles and total column from SBUV on NOAA

Donna McNamara/NESDIS (donna.mcnamara@noaa.gov) to contact Milan and agree on BUFR conversion. ECMWF can provide latest version of BUFR software (Milan Dragosavac).

Action: NESDIS

CLOSED

NESDIS to provide SBUV sample data in BUFR to ECMWF (Milan Dragosavac) and NWS-TOC (Fred Branski) for comments.

Action: ECMWF, NOAA-TOC, NESDIS

E.1.4 SeaWinds Scatterometer Data

QuikSCAT mission is to have an expected lifetime until 2010, but funding the data processing is a recurring issue. NWP centres may be requested to give their support.

# Action: NESDIS/all NWP centres

METO: We continue to lobby and have a requirement for QuikSCAT even after ASCAT becomes operational.

ECMWF: will continue to have a requirement. An email was sent by Tim Liu (NASA) on July 17 2005 announcing likely funding of QuikScat for another 4 years.

CLOSED

E.1.5.3 SSM/IS

NESDIS to pursue permission to release the data for operational use by all NWP Centres.

Action: NESDIS

## Met Office will provide NESDIS with copy of NRL authorization to distribute SSMIS data.  Met Office will clarify access for EUMETSAT and NWP centres, also including data access from future DMSP satellites.

## Action: Met Office

Consideration of where SSM/IS pre-processing should be done.

Action: Met Office, JCSDA, NESDIS

## E.1.5.4 OLS visible and thermal data

Consider the possible use of corresponding MODIS products instead of OLS.

Action: Met Office/DMI, MSC

METO: Discussions have taken place between Met Office and DMI. One proposal is to provide DWD with MODIS data once the Met Office are ingesting it operationally.

Met office response:  DMI is happy with using MODIS instead of OLS data, but the only way they were going to get MODIS in a timely fashion is with direct reception. EUMETSAT also volunteered to explore direct broadcast data from Svalbard and NOAA volunteered to supply regional MODIS from our global data set.

CLOSED: Met Office will discuss possible actions with EUMETSAT.

E.1.7.1 AQUA  AIRS+AMSU-A

Provision of clearest FOV spot (warmest, or MODIS based) from AIRS instead of centre spot is of interest for use in NWP. Parallel distribution of both data sets to be explored and confirmed.

# Action: NESDIS, Met Office

METO: Both AIRS datasets are now on the Exeter-Washington link.

## CLOSED

Meteo France will inform Met Office of need for AIRS central field of view data.  If not needed, the Met Office will liaise with NESDIS to take data offline.

Action: Meteo France, Met Office

Met Office will provide information on and clarify the availability of MODIS cloud information for the AIRS field of view, including: (1) whether it is available; (2) if there are plans to include it in the FOV dataset.

Action: Met Office

Met Office will determine if complete AMSU dataset from AQUA are provided, and requests data from NESDIS if not already.

Action: Met Office, NESDIS

## E.1.7.4 MODIS polar winds

EUMETSAT and NESDIS to continue to explore the possibility of more timely delivery of data.

# Action: NESDIS, EUMETSAT

EUMETSAT reported on current activities in making direct broadcasts MODIS winds available via EUMETCAST and potentially also on GTS.

CLOSED

Coordinate solutions for the Meteo France data access (ftp problem).

# Action: Meteo France, NESDIS, TOC

CLOSED: received data from NESDIS

To consider provision of AVHRR polar winds in order to ensure continuity after MODIS data.

Action: EUMETSAT, NESDIS

E.1.7.5 AURA: HIRDLS, MLS, OMI and TES

NESDIS will further investigate the real time availability of MLS data and offline products from TES.

### Action: NESDIS

ECMWF: Strong requirement from ECMWF to get access to MLS products in NRT.

CLOSED:  NESDIS has no plans for real-time MLS from JPL. OMI data is available in real-time from KNMI and NASA-Goddard.

1.7.7 CLOUDSAT

NESDIS will provide information on the availability of Cloudsat data (via servers), as well as plans for providing data in the future.

Action: NESDIS

E.1.8 Windsat/CORIOLIS

NESDIS to pursue with Navy the operational release of the data to NWP Centres after recovery of the instrument operations.

#### Action: NESDIS

CLOSED

Problem with communication link between NRL and NESDIS.  NESDIS will do processing locally (with NCEP fields) as it received raw data, transforms to BUFR, and distributes. NESDIS will identify a solution which meets NWP requirements.

Action: NESDIS

## E.1.9 COSMIC Radio-Occultation constellation

To provide simulated COSMIC data, based on CHAMP, in BUFR to NWP centres as soon as possible.

# Action: JCSDA, NESDIS

OPEN

NESDIS to inform WMO about COSMIC data once it is available for operational use.

Action: NESDIS

E.1.10 NPP data

All NWP centres re-iterated their requirements for a timely delivery of NPP level 1 data within 30 minutes or less. NESDIS to take note and confirm timely collection, processing and delivery of NPP data.

# Action: NESDIS

Data is expected to be received no later than 100 minutes at Svalbard with 30 minutes for processing/availability.

CLOSED

NWP centres expressed a strong requirement for early access to simulated and real NPP data for technical check-out of processing chain, data formats etc. NESDIS to pursue the availability of simulated data sets.

# Action: NESDIS

OPEN

E.1.11.1 Altimeter wave/wind data

NESDIS to explore real time access to GFO wind/wave data and to clarify with the Navy the distribution policy of the data.

# Action: NESDIS

CLOSED

NESDIS will provide information on provision and timeliness of data.

Action: NESDIS

E.2.1.2 NCEP sea-ice analysis
NCEP to confirm new sea-ice analysis data will be available in parallel with existing 12 km SST product on the GTS and the servers.

Action: NCEP

E.2.2.1 AVHRR SST retrievals

NESDIS to determine potential availability of 50 km SST product on a daily basis.

Action: NESDIS

E.2.3 Mapped AVHRR imagery

NESDIS to confirm whether production will be continued beyond winter 2005. There is still a requirement for the data at least until METOP becomes operational.

###### Action: NESDIS

METO: The Met Office has indicated there is no longer a requirement for this product.

CLOSED

E.3.1 GOES cloud-tracked VIS/IR/WV winds

SATOB data may cease, all centres to clarify if there are any other downstream users of the data.

Action: All

NWP centres have requirements to receive AMVs from GOES South America. NESDIS to clarify plans for production and availability of the data.

Action: NESDIS

The transition from GOES-10 to GOES-11 AMV is not planned to be parallel long enough for NWP centres. NESDIS to clarify the transition.

Action: NESDIS

## E.3.3 Cloud cleared radiances from GOES-E and GOES-W

Explore the possibility to move operational processing to NESDIS and provide the data over the GTS.

# Action: NESDIS

CLOSED

Clear sky brightness temperature product available operationally from NESDIS (OSDPD/SSD) server. Data not available on GTS just FTP’d from server. EUMETSAT equivalent is on GTS though. It was agreed above access is acceptable for current requirements.

## E.3.4 Digital imagery from GOES-E, GOES-W and GOES-9

Information required on any change in data volumes as a result of GOES-N implementation.

# Action: NESDIS

CLOSED

No anticipated change in data volumes.

E.4.1 NCEP SST gridded field

Parallel test data of the high resolution SST analysis is required by NWP centres prior to the operational implementation.

# Action: NCEP

CLOSED:  1/12 degree data now available. There will be a parallel transmission of new datasets. The data is already available on server, ECMWF will send e-mail with information.

E.4.4 Tropical cyclone data

There is a strong requirement for this data from the users’ community.  Data in tabular or BUFR format are available from all centres except from New Delhi.  NOAA-TOC to raise issue at WMO and clarify the generation of tabular or BUFR bulletins issued by New Delhi.

#### Action: NOAA-TOC

OPEN

TOC is continuing to pursue this action, the data is in New Delhi but has not been distributed.

E.4.5 Snow cover analysis for N. Hemisphere

Investigate the extension of coverage to the southern hemisphere (verify point of contact).

# Action: NESDIS

CLOSED

Southern Hemisphere product is automated and undergoing validation that will become available in a few months. NESDIS will notify parties when product becomes available.  POC: Ricky Irving, Sean Helfrich

Action: NESDIS

E.4.7 N. American soil temperature data

ECMWF and NOAA-TOC to liaise and establish metadata information of N. American soil temperature data.

Action: ECMWF, NOAA-TOC

OPEN

Temperature at 4 inch depths is available but not clear which stations are good so still require metadata before using. TOC continuing in efforts to establish metadata information on soil temperatures.

Action: NOAA-TOC

E.4.8 N. American ozone soundings on GTS

NOAA-TOC to provide any information on the status and availability of ozone data, in particular ozone sounding, in the USA. NCEP and TOC to report back at next meeting.

# Action: NCEP, NOAA-TOC

CLOSED

TOC is not currently receiving U.S. ozone soundings in message format and does not have contact information yet. Will continue to try and obtain sources for sounding.

Action: NOAA-TOC

# In situ surfaced based ozone data may also be available from TOC. European Centres to investigate and state requirement (daily collection of observations from past 24 hours, mainly for air quality monitoring).

#### Action: European NWP centres

METO: No Met Office requirement for real time delivery of these data.

ECMWF: interest for GEMS air quality applications.

OPEN

New Requirement – (placeholder)

To pursue delivery and release of surface-based total column and profile ozone data to the European NWPs and MSC.

Action: NOAA-TOC

E.4.10 Ground based GPS data over N. America

Provide information on availability and to explore the exchange of these data in BUFR format on GTS.

#### Action: NOAA-TOC

METO: We have a strong desire to see these data on the GTS in near real time. We understand that MSC are using these data. Similar interest from ECMWF.

### CLOSED

NCEP will explore the availability of GPS ground-based from JPL.

Action: NCEP

### NCEP will check into the ramifications of the funding problem and the potential new data from JPL.

Action: NCEP

### Plans are under consideration for a network to be established in Canada.

### 6.2	Actions related to North American requirements

N.1.1 ENVISAT-1

Discussions on data exchange have continued in the context of GEO. NESDIS encourages NWP centres to advocate the real time access to these data in North America as appropriate.

Action: European NWP centres

METO: Ongoing

CLOSED

NESDIS will provide information to WMO regarding difficulties in obtaining real-time access to altimetry and MERIS data, and request WMO to consult on this matter with ESA.

Action: NESDIS, WMO

N.3.2.3 Rain, snowfall, snow depth observations, river flow data

TOC to establish the inclusion of rain and snow depths obersvations in the synops received from Europe.

Action: NOAA-TOC

European centres to explore availability of other hydrological data such as river flow.

Action: European Centres

N.3.4.4 Automatic Dependent Surveillance (ADS) data

Plans for expansion of ADS network to be investigated. Verify the distribution of all ADS data from North America and other regions over the GTS.

Action: NOAA-TOC

CLOSED

NOAA-TOC to pursue Eastern Atlantic Gap in ADS data (East of 30W).

Action: NOAA-TOC, Met Office

N.3.6.1 Lake Temperatures

Explore the availability and provision of such in situ data globally.

Action: All

METO: No information yet will update for annual meeting.

OPEN

Include the requirement for such data in the specification of the GOS.

Action: ECMWF

Will be raised at the forthcoming ET-EGOS meeting in December in Geneva.

CLOSED

N.3.8.2 VAD Radar Winds

Met Office will update status of VAD winds data availability on GTS.

Action: Met Office

N.3.10 Ground-based GPS-Integrated Precipitable Water (GPS-IPW)

NOAA-TOC to investigate potential availability of similar data from Japan and report to group.

Action: NOAA-TOC

CLOSED

Japanese GPS IPW now on GTS in BUFR.

N.3.11 GPS Occultation Data

Convey to GFZ interest on behalf of NWPs for real-time access to data.

Action: Meteo France

### Miscellaneous Actions

M.1 Back-up of satellite Data

There is concern about possible failure of satellite data distribution on the Suitland-Exeter dedicated link.  NOAA (NESDIS and TOC), METO and M-F to investigate alternate ways to exchange data, possibly a subset of data.  POC at M-F is B. Lacroix, at METO R. Saunders, at NOAA-NESDIS B. Banks and NOAA-TOC F Branski.

Met Office to send out first draft of priority list for products on Washington-Exeter link to European centres. European NWP Centres to review product priority list.

Action: European NWP centres

METO: Product list sent out to European Centres for comment, no replies received to date.

CLOSED

M.

Backup processing for ATOVS data in Europe to be considered.

Action: EUMETSAT, Meteo France, Met Office

Some provision and backup is provided through the EUMETSAT EARS system. EUMETSAT considering how to process global dumps as a backup in operations.  For the short term, the Met Office proposes to use the Internet as a backup for ATOVS data.

M.

Met Office to distribute an updated priority list for products on Washington-Exeter link to all.

Action: Met Office

M.2 Satellite data volume

Met Office and ECMWF to update satellite data volume projections for planning purposes (telecommunication, data ingest, archiving). The expected large data volumes to be reviewed at the next meetings.

# Action: All

METO: Roger Saunders will update his satellite data volume plan in Jan 2006 and circulate to the group.

ECMWF: ongoing

OPEN

Volume updates were provided at the 19th Meeting and the evolving data volumes will continue to be monitored.

Action: Met Office, ECMWF

M.3 NPOESS/Metop data format and code transition

Proposals for information contents in BUFR from NPP/NPOESS to be coordinated between NESDIS and NWP Centres, NESDIS to issue first proposals.

Action: NESDIS, NWP centres

CLOSED

Requirements for BUFR recognized.

M.4 Altimeter wave/wind data

NESDIS to clarify with the Navy the distribution policy of the data.

#### Action: NESDIS

CLOSED

M.5 Data and products on NESDIS servers

Readily available description of data on NESDIS servers to be provided to NWP centres.

# Action: NESDIS

CLOSED: URL provided by NESDIS.

## M.6 Profiler/VAD-wind data formats

All data providers to be encouraged to make the data available in agreed WMO BUFR formats.

# Action: NOAA-TOC, Met Office/Eumetnet

METO: See message below from Myles Turp:

Weather Radar Wind Profiler data (WRWP) are already available on the GTS from some European countries. There are currently discussions within the EUMETNET OPERA Community to standardise the data format. Although a standard set of descriptors is available they are being interpreted in different ways which can lead to problems storing these data.  Also many countries are using a pictorial GTS Bulletin header which can lead to storage problems as the messages contain binary data. This will change as an agreement has already been made to change all WRWP messages to binary headers. Action is now with each countries National Met Centre's to ensure that this takes place.  CLOSED

M. Washington-Exeter link

Review capacity in light of expected increase in data volumes.

Action: Met Office, NOAA-TOC

METO: This has been done prior to adding a second AIRS stream on the link. We will continue to review the situation.

OPEN

M. Existing satellites requirement review

NWP centres and the WMO will review availability of data from existing satellite missions for global environmental monitoring applications.

Action: All

M. North American Requirements Table

MSC will compose a table for North American Requirements similar to the table in the European Requirements document.

Action: MSC

CLOSED (was accomplished during the meeting)

M.

MSC will provide more information on SWIFT/CHINOOK.

Action: MSC

M.

NWP centres to explore interest in the CHINOOK data in near real-time.

Action: All

M.

Review the requirements for oceanographic data for NWP, and explore their timely availability for near-real-time ocean analysis. This should be brought to the attention of the appropriate WMO expert teams.

Action: ECMWF, WMO

M.

NCEP will determine requirement for surface current measurements using feature tracking of ice or ocean currents.

Action: NCEP

M. Mid-term review of actions

ECMWF to co-ordinate the mid-term review of actions from European side, NOAA and MSC from North American side. The written review will be followed up with telephone conference.

#### Action: ECMWF, NOAA/MSC

M. Next meeting

Next meeting to be arranged in spring 2007 in Darmstadt by EUMETSAT. POC is Kenneth Holmlund.

Action: EUMETSAT

### 6.4	Points for information

I.1 POC at Met Office for VAD winds is Myles Turp (Myles.Turp@metoffice.gov.uk)

Further information can be found at: http://www.metoffice.gov.uk/research/interproj/cwinde/wradar/index.html

http://www.metoffice.gov.uk/research/interproj/cwinde/index.html

Nigel Atkinson is POC for ATOVS.

I.2 POC at NESDIS

NESDIS Office of Satellite Data Processing and Distribution:

POCs for this Office are: Gene Legg, Barbara Banks, Reginald Lawrence (Level 1b and IT infrastructure).

Antonio Irving is the POC for OSDPD products and services.

Luisa Blanchfield is the POC for the NOAA-NESDIS Office of International and Interagency Affairs.

I.3 POC at NCEP

Robert Grumbine is POC for sea-ice analysis.

William Gemmill is the POC for SST analysis.

Bradley Ballish is the POC for MDCRS.

Brent Gordon is the POC for gridded products.

I.4 POC at ECMWF

Dragan Jokic is POC for gridded products.

Milan Dragosavac is POC for data formats.

I.5 POC at NOAA-TOC

POC is Fred Branski.