## Sheet1
Tracking Number | Task | Tasker | Update | POC | STATUS | Additional Comments
From 19th Session
E.1.7.5 | AURA: HIRDLS, MLS and TES NESDIS will further investigate the real time availability of MLS data and offline products from TES. | NESDIS to provide update, need to get raw data to NSOF. | The MLS ozone and temperature data are produced in near-real-time with a latency of typically between 2 to 4 hours. The data sets can be accessed at the following sites via anonymous FTP ftp://satepsdist1e.nesdis.noaa.gov/mls/ozone and ftp://satepsdist1e.nesdis.noaa.gov/mls/temp The TES and HIRDLS products are currently unavailable at NESDIS SPP servers. Detailed info is needed to get the data into NSOF. | John Paquette, Han Jun Ding | Recommend Closing | MLS – micro-wave limb sounder; TES - Tropospheric Emission Spectrometer.
E.1.8 | Windsat/CORIOLIS Transformation to BUFR and distribution to be clarified. NOAA will identify a solution which meets NWP requirements. | NESDIS to look into doing the processing (to include radiances) and providing data operationally. | Windsat data in BUFR (formatted by NWS) are available from our Distribution Server. Users are requested to apply for the data using the supplied form. Due to limited resources, data access from NESDIS’s Data Distribution Server is evaluated on a case by case basis. Also, due to limited resources, NESDIS does not have the capability for additional processing of data to support 24x7 operations. | John Paquette | Recommend Closing
E.1.10 | NPP data NWP centres expressed a strong requirement for early access to simulated and real NPP data for technical check-out of processing chain, data formats etc. NESDIS to pursue the availability of simulated data sets. NOAA has a standing request to the IPO for early access to NPPx DRs. | NESDIS to update group on early availability of data sets, CrIS & ATMS in particular. | The IPO is continuing to work with DOD and the DoS to achieve clearance for all external users to have routine access to sample/simulated data. In the interim, sample data sets of CrIS and ATMS EDRs will be provided at the NAEDEX meeting in a DVD as requested. Other data on the DVD include VIIRS, CrIS, and ATMS SDRs. | John Paquette | Recommend Closing
E.1.11.1 | Altimeter wave/wind data NESDIS will provide information on provision and timeliness of data and to explore possibilities for further distribution. | JASON processing to be turned over to NESDIS in Oct 2008. NESDIS to pursue availability of data from GFO (GEOSAT follow on). | JASAON-2 NESDIS/OSO officially transferred JASON2 processing system to NESDIS/OSDPD in November 2009. The products are produced and distributed on NESDIS/ESPC operational system with timeliness of 3 hours for 75%; within 5 hours for 90%. The best info on real-time Jason-2 data access is found at http://www.osdpd.noaa.gov/ml/ocean/J2_handbook_v1-4_no_rev.pdf GFO (GEOSAT Follow On) NEDIS/STAR collected Geophysical Data Records (GDRs) from Geosat Follow-On, and provided the GDRs via non-anonymous ftp to any users, foreign or national. The mission concluded a year ago, with the last data collected in mid-September 2008. The data can be access from the following website: http://ibis.grdl.noaa.gov/SAT/gfo | Hanjun Ding | Recommend Closing
E.2.1.2 | NCEP sea-ice analysis NCEP to confirm 1/12 degree sea-ice analysis data will be on the GTS and the servers in addition to the 1/12 degree SST data. NCEP/CIO to confirm the continued availability of the 0.5 degree sea-ice/SST data on the GTS. NCEP: Both the 1/12 and 0.5 degree global SST data are available on GTS and on NCEP public data servers. NCEP has no plans to discontinue the 0.5 degree product and will continue to do so until all users are utilizing the higher resolution products. Both products are available on the NCEP public data server at: ftp://ftpprd.ncep.noaa.gov/pub/data/nccf/com/omb/prod/sice.{YYYYMMDD}/ where YYYYMMDD is the current date. The 0.5 degree product is available on GTS with header OTLA88 KWBI and the 1/12 degree product is available with header ETWA88 KWBI. | NCEP plans to make data available under heading EEWA88 KWBM in November/December time frame. TOC/UKMO to distribute. | There was a slight glitch on our end that prohibited the product from being transmitted since sometime this past summer. The problem has been fixed and the data is being distributed. | Michelle Mainelli | Recommend Closing
E.4.4 | Tropical cyclone data There is a strong requirement for this data from the user community. Data in tabular or BUFR format are available from all centres except from New Delhi. NOAA-TOC to raise issue at WMO and clarify the generation of tabular or BUFR bulletins issued by New Delhi. TOC is continuing to pursue this action; the data is in New Delhi but has not been distributed. | Inquire with Walter Smith at TOC |  | Yana Gevorgyan | OPEN | Contacted Walter Smith at TOC
E.4.7 N. | American soil temperature data Temperature at 4 inch depths is available but not clear which stations are good so still require metadata before using. TOC continuing in efforts to establish metadata information on soil temperatures. | TOC to establish metadata information on soil temperatures. |  | Fred Branski Yana Gevorgyan | OPEN | Inquiry sent to Walter Smith at TOC
E.4.10 | Ground based GPS data over N. America NCEP will confirm the availability of GPS ground-based from JPL. Action: NCEP NCEP will check into the ramifications of continued funding and the potential new data from JPL. Action: NCEP Note: Plans are under consideration for a network to be established in Canada. NCEP: Ground based GPS data are available from JPL as a part of the IGS project (http://igscb.jpl.nasa.gov/). These data are the raw carrier range and phase information, global in nature, and available with as much as a one hour delay. NOAA has not yet identified the funding sources to convert these data into the wet and dry atmospheric components that are available today over the continental US GPS locations. At this point in time, this work has been pushed back to at least 2010. | Funding issue, NCEP working requirements and availability of data to wider community. New action: verify distribution and conversion of data into standard WMO BUFR format. | The data from JPL can only be received for a cost. The only other GPS data NCEP receives operationally and resends out through the TOC is the Integrated Precipitable Water. The NOAA Office of Oceanic and Atmospheric Research (OAR) has an agreement with the NWS NCEP to provide GPS moisture retrievals in BUFR format applicable to NCEP’s version at 30 minute intervals. These moisture values are assimilated into NCEP’s NWP models. The NCEP BUFR formatted products are also available on the GTS via the WMO Header, “ISXT40 KBOU.” Additional funding is needed to transition the products from research to a 24x7 operation that includes generation and dissemination of a WMO BUFR format. OAR is collaborating with NESDIS and the NWS in pursuing funds to transition the products to operations. OAR is using the NESDIS SPSRB process to introduce the funding request for NESDIS management review. | Michelle Mainelli John Paquette | Recommend Closing
From 20th Session
E.x | MODIS imagery data EUMETSAT to explore with NESDIS the provision of a subset of MODIS imagery data from NESIDS to EUMETSAT for re-transimission via EUMETCast. | EUMETSAT to implement to processing and make data available, likely by end of 2008. | Update pending. | Hanjun Ding | OPEN
E.x | Snow cover analysis for S. Hemisphere Southern Hemisphere product is automated and undergoing validation that will become available in a few months. NESDIS will notify parties when product becomes available. | Experimental data available on a web site. NESDIS to provide URL. | The automated SH snow and ice products are now operational in GRIB2 and can be accessed using NESDIS’s Data Distribution Server. Users are requested to apply for the data using the supplied form. Due to limited resources, data access from NESDIS’s Distribution Server is evaluated on a case by case basis. NESDIS is pursuing the alternative of making these products accessible from the GTS in the future. | John Paquette | OPEN
E.x.N | American ozone soundings on GTS To pursue delivery and release of surface-based total column and profile ozone data to the European NWPs and MSC. Action: NOAA-CIO TOC is not currently receiving U.S. ozone soundings in message format and does not have contact information yet. Will continue to try and obtain sources for sounding. | NOAA to survey research community for possible sources of data. | Need to discuss with NOAA-CIO, recommend to resign | Hanjun Ding | OPEN
N.x | Sea surface temperature, wind direction/speed, wave height, sea ice analyses and forecast products. Action EU centres to clarify data availability. Action: European NWP centres METO : Met Office is part of the GHRSST project and produces an operational SST analysis OSTIA. Details at: http://ghrsst-pp.metoffice.com/pages/latest_analysis/ostia.html Also note data available from OSI-SAF see: http://www.osi-saf.org/index.php | CMC & NCEP to determine if web availability is sufficient or if GTS distribution is desired. | NCEP still has a requirement to automate the retrieval of the data files from UKMO. The web availability will not suffice. | Michelle Mainelli | Recommend Closing
N.x | AVHRR winds EUMETSAT is planning the derivation of Atmospheric Motion Vectors with AVHRR. Sample data sets to be provided to all interested NWP centres when available. | Update status to note that we have products available through GTS and to provide instructions on how to access them. | The respective WMO headers are: NOAA-15 JCVX91 KNES YYGGgg NOAA-16 JCVX92 KNES YYGGgg NOAA-17 JCVX93 KNES YYGGgg NOAA-18 JCVX94 KNES YYGGgg NOAA-19 JCVX95 KNES YYGGgg METOP JCVX97 KNES YYGGgg | John Paquette | Recommend Closing
M.x | NWP requirements for data WMO will provide parties with the latest status of requirements and the appropriate references. As presented at the 20th meeting the WEB-site has been updated and the requirements database is in the process of being updated. WMO to update requirements database and to report at next meeting. |  |  | Fred Branski | OPEN
M.x | Washington-Exeter link Met Office to distribute an updated priority list for products on Washington-Exeter link to all. Action: Met Office METO: Met Office is in process of gathering an updated list. Will circulate when responses from all European centres received. Review capacity in light of expected increase in data volumes. Action: Met Office, NOAA-CIO METO: Currently the link is adequate for the data volumes but we will continue to review this. Notable delays on text and binary links observed in 2007. Met Office and CIO to investigate and to move COSMIC data to NESDIS link. Action: Met Office and CIO METO: The COSMIC data has been moved from WMO GTS/MTN link to the NESDIS link. The WMO GTS/MTN link to Washington has been upgraded in the US to UK direction and there are plans to upgrade the link in the UK to US direction. | Limited capacity is hindering exchange of data, and preventing addition of some new data sets. METO to increase bandwidth. NOAA is pursuing joining RMDCN |  | Fred Branski | OPEN
M.x | AMSU A1, A2, MHS, HIRS/4 and AVHRR Currently NESDIS is distributing full orbits. NWP centres to review requirements for reception of granulates for improved timeliness. Action: All NWP centres METO: We can see some advantages in this if timeliness of the data is improved. Can the timeliness improvement be quantified? There would need to be changes to the European distribution of ATOVS data if this went ahead. DWD: Interest in improved timeliness ECMWF: The current timeliness of the full orbit dissemination is sufficient. MSC: Gains in timeliness would be appreciated. NCEP: Would find the availability of “granulates” very useful in our assimilation process, assuming the come earlier. | NESDIS to check and report on availability & distribution | Level 2 full orbital sounder retrievals in BUFR are available from NOAA-15, NOAA-18, NOAA-19, and Metop-A on the GTS. The products are available three hours from the end time of the pass, per current international requirements. NESDIS is pursuing improvements in product timeliness when additional downlink sites are installed in the NPP and NPOESS eras. The WMO headers for the 50 km resolution products are: IUTX01 KNES YYGGgg…IUTX09 KNES YYGGgg. The WMO headers for the 120 km resolution products are: IUXA01[-99] KWBC YYGGgg, IUXB01[-99] etc., IUXC01[-99], IUXD01[-99], IUXI01[-99], IUXJ01[-99], IUXK01[-99]. | John Paquette Hanjun Ding | Recommend Closing
1.2 1.3 | Points of Contact at NESDIS, NWS and NCEP Updated POCs are: NESDIS: John Paquette Han Jun Ding Vincent Tabor Yana Gevorgyan NCEP: Michelle Mainelli | OSDPD products and services: Antonio Irving GOES Clear Sky Radiances - Curtis Holland Sea-ice analysis: Robert Grumbine SST analysis: William Gemmill MDCRS: Bradley Ballish | Sea-ice analysis: Robert Grumbine SST analysis: Robert Grumbine Aircraft and radiosondes: Bradley Ballish | Yana Gevorgyan | Recommend Closing
From 21st Session
E.1.2.5 | AVHRR polar winds NESDIS to make data available. Current planned date is Nov 08. |  |  | John Paquette | OPEN
E.1.4 | SeaWinds Scatterometer Data. NESDIS to provide one month notice prior to data availability to allow NWP centres to prepare. |  | The WMO header for QuikSCAT 12.5 km winds in BUFR are: ISXXii KNES, where ii is the region number. Users are requested to apply for the data using the supplied form. Due to limited resources, data access from NESDIS’s Distribution Server is evaluated on a case by case basis. The Scatterometer on Ocean2 was launched on September 23, 2009; the operational phase starts after 9 months post-launch. Global scatterometer data at Level 1B, 2A, and 2B to be provided by ISRO, orbit by orbit, for operational use within 180 minutes of collection on the spacecraft for the duration of the mission. The Scatterometer on GCOM-W is scheduled to be launched on November 2011 by JAXA. | John Paquette Hanjun Ding | Recommend Closing
E.1.5.2 | SSMI Radiance data NESDIS to investigate recurring outages based on input from EUMETSAT. Outage dates already provided by EUMETSAT. MSC may be able to provide additional outage info. | NESDIS to investigate recurring outages based on input from EUMETSAT. | F13 and F15 operated in a single recorder mode lately for several occasions due to technical issues, and schedule conflicts (low priority), which caused some expected some missing orbits and data outages. | Hanjun Ding | Recommend Closing
E.1.5.3 | SSM/IS. NESDIS to approach NRL about early access to data, during calibration/validation. | NESDIS to approach NRL about early access to data, during calibration/validation. | FNMOC was contacted about the possibility to have SSM/IS earlier than Feb 2010 when the SSM/IS EDR/TDR/SDR data is scheduled to be delivered to NESDIS. | Hanjun Ding | Recommend Closing
E.1.7.4 | NESDIS to investigate NRT access to MLS ozone & humidity products. |  | The MLS ozone and temperature data are produced in near-real-time with a latency of typically between 2 to 4 hours. The data sets can be accessed at the following sites via anonymous FTP ftp://satepsdist1e.nesdis.noaa.gov/mls/ozone and ftp://satepsdist1e.nesdis.noaa.gov/mls/temp The MLS humidity products are currently unavailable in NRT system. | Jogn Paquette Hanjun Ding | OPEN
E.1.9 | COSMIC. NESDIS to investigate availability of SAC-C data. |  | We are working with CONAE in Argentina, and are working along with NASA to see if we can provide ground station support a Fairbanks AK so that we can downlink SACC data every couple of hours. The data has been tested by the NOAA GPS RO scientist, Lidia Cucurull, and is of comparable quality to COSMIC. We expect to do a test downlink support at Fairbanks over the next couple of weeks. Please let me know if you have any other questions. | Yana Gevorgyan | OPEN | This Item will not be updated further prior to the meeting.
E.1.11 | NPP. NESDIS to report on how operational access to data will be addressed and respond to Euro request to be involved in calibration/validation. | NESDIS to report on how operational access to data will be addressed and respond to Euro request to be involved in calibration/validation. | Operational SDR and EDR data will be available from the IDPS/NDE. NOAA/NESDIS welcomes users to participate in the Cal/Val period prior to operational declaration of NPP; IPO will collaborate with EUMETSAT to establish a joint Cal/Val plan. | John Paquette | Recommend Closing
E.1.12 | OCO. NESDIS to investigate possibility of cooperation with NASA to make data available. | NESDIS to investigate possibility of cooperation with NASA to make data available. | On February 24, 2009, OCO failed to reach orbit. | Yana Gevorgyan | Recommend Closing
M.x | To complete the updated requirements table. ECMWF & NOAA/CIO. | To complete the updated requirements table. ECMWF & NOAA/CIO. |  | Fred Branski | OPEN