## Flash Flood Services
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Quantitative Precipitation Estimates/Short-Term QPF
1. Improving precipitation source data
| a. Improve Quantitative Precipitation Estimation Algorithms by including Dual-polarization radar estimation algorithms. | complete | G2 | ??? | on-going | stage 3 | ???
| i. Adapt NEXRAD Precipitation Processing System (PPS) for dual polarization radars. | complete | G2 | ??? | on-going | stage 3 | ???
| b. Improve Quantitative Precipitation Estimation Algorithms by including Terminal Doppler Weather Radar (TDWR) data. | complete | G2 | ??? | on-going | stage 3 | ???
| c. Mitigate the effects of bright-band contamination by providing Range Corrections and Convective Stratiform Separation capabilities into the WSR-88D and AWIPS MPE systems. | on-going | stage 2 | FFS
d. Distribute Digital Hybrid Reflectivity (DHR) and Digital Storm Total Precipitation (DSP) products in real-time to all WFOs with CWAs covered by the radar
2. Improve precipitation estimation and forecsat procedures
a. Upgrade the NEXRAD PPS so that it can support multiple new Volume Coverage Patterns (VCP), negative elevations, higher resolution data from the RDA, and migration to Linux
| b. Evaluate NSSL’s National Mosaic of QPE (NMQ) as input to FFMP | complete |  | FFS | complete |  | FFS | on-going |  | FFS
| i. Establish computing hardware and infrastructure at NWS facilities to support NMQ generation for ingest by FFMP. | complete |  | FFS | complete |  | FFS | on-going |  | FFS
| ii. Create and disseminate NMQ products on a Cartesian grid of 1-km resolution updated every five minutes for ingest by non-radar centric FFMP applications. | complete |  | FFS | complete |  | FFS | on-going |  | FFS
| iii. Create and disseminate one-hour statistical extrapolative QPF on a Cartesian grid of 1-km resolution updated every five minutes for ingest into FFMP. | complete |  | FFS | complete |  | FFS | on-going |  | FFS
c. Enhance the MPE to support WFO Flash Flood Services.
| i. Integrate existing Western Region Mountain Mapper Daily QC functionality and OHD MPE application functionality into a single set of nationally supported operational applications. | complete | G2 | FFS | on-going | stage 3 | FFS
| ii. Integrate existing ABRFC P3 and OHD MPE application functionality into a single set of nationally supported operational applications. This includes alternate methods for generating multi-sensor precipitation and additional interactive quality control methods including a more powerful polygon edit feature. | complete | G2 | FFS | complete | Gate 3 | FFS | on-going | stage 4 | FFS (SAE?)
| iii. Integrate satellite information into MPE calculations | complete | G2 | FFS | on-going | stage 3 | FFS
iv. Improve speed and efficiency of MPE field generating processing to facilitate more frequent runs, and for time spans shorter than one hour.
v. Provide the forecaster graphical editing tools to quality control and edit the point data and gridded precipitation estimates in order to produce the highest quality point gage data and gridded fields.
vi. Provide automated mosaicking of radar estimates.
| vii. Provide automated rain gauge quality control | on-going | stage 2 | FFS
| viii. Increase MPE space/time resolution to 1 degree x 1 km and less than 1 hour precipitation refresh; Enhanced MPE (EMPE) | complete | G2 | FFS | on-going | stage 3 | FFS
| ix. Enhance the rainfall nowcasting algorithm to produce short range (0-3 hours) regional, multi-sensor gridded precipitation forecasts using MPE-WFO products; Multisensor Precipitation Nowcaster (MPN). | complete | G2 | FFS | on-going | stage 3 | FFS
x. Integrate HydroView in D2D
| xi. Provide North-American Scale Remote Sensor Precipitation Estimator capability | on-going | stage 2 | FFS
d. Develop the next generation of precipitation estimation (Q2) that promotes the best features of OHD and NSSL’s multi-sensor precipitation estimation methods.
i. Conduct an assessment/inter-comparison of the two multi-sensor precipitation estimation methods.
| ii. Develop a collaborative Q2 precipitation estimation (TAR River Basin Project) | on-going | stage 1 and 2 | ???
iii. Enhance Q2 to address outstanding operational, science, and science-to-operations needs for QPE
iv. Provide operational testing of Q2.
v. Provide operational framework that identifies the role of the WFO, RFC and NSSL in the production and use of next generation precipitation estimation.
3. Quantify precipitation estimation uncertainty
| a. Develop radar-based Ensemble/Probabilistic Quantitative Precipitation Estimation (PQPE) as a measure of the uncertainty of Quantitative Precipitation Estimation and support operational decision making. | on-going | stage 2 | FFS
| b. Provide a measure of uncertainty in the manually produced HPC 6 and 24-hour Quantitative Precipitation Forecast. | complete |  | FFS | complete |  | FFS | complete |  | FFS
Flash Flood Guidance
1. Improve FFG System Performance
| a. Remove threshold runoff information gaps inside a single RFC’s area of responsibility | on-going |  |  | on-going |  |  | on-going
| b. Fix overlapping values of FFG along the shared border between neighboring RFCs. | on-going |  |  | on-going |  |  | on-going
| c. Fix inconsistent gridded FFG across adjacent RFC boundaries. | on-going |  |  | on-going |  |  | on-going
d. Create Tools to manually edit FFG product before dissemination
e. Improve gridded Threshold RunOff (TRO) derivation
2. Enhance Archive of critical FFG data
a. Improve Storm Data archived information to include corresponding RFC and more specific county/river basin location if available.
b. Utilize all available information from existing USGS gage networks including the existing crest-stage gage network used to establish flood frequencies of small streams and include in Storm Data.
c. Archive both RFC precipitation input used to determine FFG and WFO precipitation input used in FFMP to determine if inherent problems exist in using precipitation input from two different sources.
d. Separate flash flood storm types as either over bank (appropriate to use FFG), mountainous terrain, or urban inundation in Storm Data.
3. Develop FFG Verification Program
Basin Legacy Support
1. Establish a National Basin Repository of FFMP GIS datasets
| a. Establish a National Basin Repository computer server hardware and communications infrastructure to allow access to the FFMP GIS datasets. (complete) | complete |  | FFS | complete |  | FFS | complete |  | FFS
| b. Create a seamless high quality hydrologically-connected FFMP basin and stream dataset for the United States, including Alaska, Hawaii, Puerto Rico, and Guam. | complete |  | FFS | complete |  | FFS | on-going |  | FFS
| c. Implement software for web interface to FFMP GIS dataset. | complete |  | FFS | complete |  | FFS | on-going |  | FFS
d. Create instructions for users to download data and prepare it for localization in AWIPS. The instructions will also detail how WFOs can incorporate previously customized basins into the files obtained from the national repository.
e. Disseminate instructions to WFO staff.
f. Train WFO staff on accessing FFMP GIS datasets through the National Basin Repository.
2. Provide radar centric FFMP Basins GIS datasets
| a. Create radar centric FFMP Basins GIS datasets for CONUS Sites (complete) | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | Training
| b. Create radar centric FFMP Basins GIS datasets for OCONUS Sites (complete) | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | Training
| c. Provide radar centric FFMP Basins GIS datasets for new radars as radars are added to the operational network | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | Training
| d. Enhance radar centric FFMP Basin GIS datasets to include hydrologic connectivity (complete) | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | Training
| e. Provide Basin Customization documentation and training. (complete) | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | Training
| f. Provide Basin Customization Support and Data Access (ongoing) | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | Training
| g. Update Basin Customization scripts from Avenue (supported in ArcView 3.X) to Visual Basic (supported in ArcGIS 9.0) (ongoing) | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | FFS | complete |  | Training
h. Create a functionality to include latitude/longitude delineation of customized basins for use in GIS-based flash flood warnings
Flash Flood Monitoring and Prediction
| 1. Provide Basin Layering capability | complete |  | FFS | complete |  | FFS | complete |  | FFS
| 2. Provide Basin Trace Capability | complete |  | FFS | complete |  | FFS | complete |  | FFS
| 3. Add multiple monitoring time frames and thresholds | complete |  | FFS | complete |  | FFS | complete |  | FFS
4. Provide multiple radar service back up capabilities.
| a. Allow FFMP to ingest non-dedicated radar data. | complete |  | FFS | complete |  | FFS | complete |  | FFS
| b. Allow WFOs the ability to obtain the basin customization data for non-dedicated radar sites. | complete |  | FFS | complete |  | FFS | complete |  | FFS
| 5. Archive precipitation accumulation data in a format compatible with Weather Event Simulator playback capability. | on-going | OSIP Stage 2 | FFS
| 6. Monitor rainfall in FFMP with gridded, high resolution multi-sensor mosaicked data. Initial assessment with NSSL’s National Mosaic QPESUMS (NMQ) and OHD’s Enhanced MPE | on-going | OSIP Stage 2 | FFS
| 7. Enable multiple user-selectable inputs (e.g. DHR, EMPE, NMQ) | on-going | OSIP Stage 2 | FFS
8. Integrate nowcasting capability (with MPN) into FFMP
| 9. Provide the ability to monitor multiple guidance values in FFMP. | on-going | OSIP Stage 2 | FFS
10. Adapt FFMP to interpret precipitation estimates and forecasts expressed as probabilities, as well as those expressed as deterministic amounts.
11. Integrated FFMP into the Next Generation Warning Tool where basins or groups of basins are easily identified and selected to quickly produce flash flood warnings.
12. Expand FFMP capabilities to create digital/graphical Flash Flood Products
Relative Flash Flood Potential Index
| 1. Develop a static relative Flash Flood Potential Index as a function of slope, vegetation, soil type and land use for the entire conterminous U.S. | on-going | stage 1 and 2 | FFS | on-going | stage 3 | FFS
| 2. Enhance the relative Flash Flood Potential Index to include a dynamic soil moisture component. | on-going | stage 1 and 2 | FFS
| 3. Provide ability through standard AWIPS delivery (either D2D or FFMP) to view the Relative Flash Flood Potential Index. | on-going | stage 1 and 2 | FFS
Statistical Distributed Modeling
1. Investigate the use of a statistical distributed model as a means to improve accuracy and lead time of flash flood forecasts.
| a. Develop methods and procedures to create simulated flood frequency information for each model element using a distributed model and an archive of historical data. | complete | G2 | FFS | on-going | stage 3 | FFS
| b. Develop methods and procedures to use the simulated flood frequency information with distributed modeling to produce flash flood information. | complete | G2 | FFS | on-going | stage 3 | FFS
c. Ingest forecast grids from MPN into the statistical distributed model in an effort to improve flash flood forecasting lead times.
2. Investigate the use of probabilistic Quantitative Precipitation Estimates with the Statistical Distributed Model as a means to generate probabilistic FFG.
a. Develop methods and procedures to incorporate probabilistic Quantitative Precipitation Estimates into the statistical distributed model to produce probabilistic flash flood information.
b. Develop methods and procedures for probabilistic flash flood information to be ingested into and used by FFMP.
Site Specific Hydrologic Predictor
1. Provide software tools to support the model calibration at the 1 hour temporal resolution and smaller spatial resolution of the SSHP/SAC-SMA model.
2. Provide methods and procedures to integrate the variational assimilation (VAR) state adjustment function into the SSHP/SAC-SMA in an effort to maintain proper model state variables.
3. Integrate snowmelt modeling techniques to the SSHP/SAC-SMA model.
4. Integrate routing techniques to the SSHP/SAC-SMA model.
Evaluation of other Hydrologic Models
| 1. Evaluation of Hydrologic Forecasts in Peurto Rico based on the use of USGS hydrologic models. | on-going | stage 2 | ???
Hydraulic Modeling and Analysis Tool
1. Enhance the Dambreak Catalog Reviewer and Estimator (DAMCREST)
a. Validate current Dambreak Catalog used in DAMCREST
b. Validate current simplified hydraulic models used in DAMCREST
| c. Add the current rule of thumb methods used by field offices to DAMCREST. | on-going | ??? | ??? | on-going | ??? | ???
d. Add the regression component that is currently in the CBRFC catalog to DAMCREST as a measure of comparison.
e. Interface DAMCREST with National Inventory of Dams to provide RFC/WFO with the most up to date dam information.
| 2. Develop an application Dam Analysis Tool (DamAT) to automate the functionality of the DAMCREST, the FLDWAV Cross Section Tool (FLDXS) and the flood wave viewer (FLDVIEW) to provide timely and accurate dam failure forecasts. | on-going | stage 2 | ??? | on-going | stage 2 | ???
a. Add the current rule of thumb methods used by field offices to DamAT.
b. Add the regression component that is currently in the CBRFC catalog to DamAT as a measure of comparison.
c. Add the Breach erosion model (BREACH) component DamAT to improve dam breach parameters.
d. Expand DamAT to include simplified dynamic routing to improve dam failure forecasts.
| 3. Quality control critical input data (dam and town location, dam and reservoir information, field boundaries for the dams) | on-going | stage 2 | ???
4. Provide operational database interaction capability to exchange dam break information between RFC/WFO/OHD/OCWWS/Regions.
5. Provide operational framework policy for RFC and WFO dambreak analysis and forecast issuance.
Training
1. GIS Training - Provide a basic GIS course for RFC forecasters and WFO Hydrologic Program Managers. The course content should include the background to understand and use GIS with regard to hydrology.
2. FFG Training - Provide a basic hydrologic science course for RFC forecasters and WFO Hydrologic Program Managers. The course content should include the scientific background to understand and use FFG. Specific subject matter should include underlying science and implementation of FFG, strengths and limitations of FFG, how FFG should be used to address flooding in urban and mountain areas, how the science and implementation of FFG are advancing.
3. FFMP Enhancement training - Provide a FFMP enhancement training for WFO Hydrologic Program Managers and forecasters. The course content should include the scientific background to understand and use FFMP. Specific subject matter should include underlying science and implementation of FFMP and how the science and implementation of FFG are advancing.
4. Basin Customization - Provide Basin Customization training for WFO Hydrologic Program Managers. The course content should include the skills and tools needed to customize high resolution basins that have been delineated for use with the FFMP application included in AWIPS. Specific subject matter provide the trainee skills to identify, create, alter, and redefine basins to better support local flash flooding needs.
5. Flash Flood Hydrology and QPE Workshop - Provide Flash Flood Hydrology and QPE Workshop for WFO Hydrologic Program Managers. The course content should include Flash Flood Guidance and the hydrometeorology of flash floods. Specific subject matter should include strengths and limitations of Flash Flood Guidance, events which can lead to the onset of flash flooding, the use of the FFMP application as a decision-making tool during heavy precipitation events; and use case studies as training tools.
6. Hydraulic Modeling Operations - Provide a hydraulic modeling operations course for WFO personnel. The course content should include the necessary skills required to perform hydraulic operations.
a. Develop a tutorial that explains how to run the Simplified Dam Break model including data acquisition (i.e., cross-section selection and the selection of dam break parameters).

## S2LT Det - Lumped
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Hydrometeorological Inputs
1. Develop an NDFD preprocessor in NWSRFS to provide RFC access to other hydrometeorological inputs.
2. Add the capability to use WFO, HPC or model QPF.
| 3. Support NOHRSC activities to augment snow water equivalent data for Alaska. | [6 empty] | on-going |  | ???
4. Mitigate inconsistencies between calibration, observation and forecast computations of hydrometeorological inputs.
a. MAT
b. MAP
c. Evapotranspiration
5. Dynamically include stranger reports in the MAP computation when available.
6. Create new sources of Potential Evapotranspiration estimates as current methods are becoming obsolete.
a. Satellite based estimates of surface net radiation
b. Combined satellite/ground-based cloud cover estimates as a replacement for the ‘sky cover’ observations used in the pre-ASOS computation of potential evapotranspiration.
7. Improve temperature forecasts
a. Identify optimum methodologies for spatial and temporal interpolation of temperature observations and forecasts to grids
| b. Derive new conversion weights, or validate adequacy of existing weights, for western region. | complete | G1 | S2LT | on-going | stage 2 | S2LT
| c. Examine NDFD, NAM forecasts grids to determine any biases relative to historic point temperature data. | on-going | stage 1 | S2LT
Hydrologic Modeling: Calibration System Enhancements
1. Mitigate inconsistencies between USGS historical mean daily flows used in calibration, versus the operationally available data.
2. Automate procedures to acquire needed data for calibration.
3. Provide options for 1-hour, 3-hour, and 6-hour calibration statistics within NWSRFS.
| 4. Evaluate the impacts of historical data quality control procedures (specifically IDMA) on hydrologic model calibration. | on-going | stage 1 | ???
| 5. Re-implement the Interactive Calibration Program (ICP) using a more modular design better enabling the addition of new features in the future. | complete | G2 | SAE | complete | G3 | SAE | on-going | stage 4 | SAE
6. Enhancements to re-implemented ICP
a. Provide graphical statistical enhancements per Eric Anderson report.
b. Provide capability to directly edit time series from the PLOT-TS window in ICP.
c. Provide additional ICP functionality for modifying Unit Hydrographs
d. Provide ICP enhancements to support analysis of Snow Area Depletion Curve
e. Provide ICP enhancements to provide a display of a time lapse of Sacramento model states.
f. Add AB_OPT functionality into ICP
7. Develop new architecture/GUIs to streamline the existing calibration system programs. This should combine the functions in the existing programs such as the Calibration Assistance Program (CAP), the ICP, the Interactive Double Mass Analysis (IDMA), the Air Temperature Plotting program (TAPLOT), PXPP, MAP, MAT, MAPE, etc…
8. Provide a link between the interactive calibration program and the automatic calibration procedures.
9. Incorporate multi-objective automatic optimization methods for model parameter calibration
Hydrologic Modeling: Deterministic Forecasting
| 1. Evaluate the need to use energy budget snow models versus SNOW-17 models. | on-going | stage 1 | S2LT
2. Investigate methods to improve SNOW-17
| 3. Develop plan and approach to use SNODAS output to generate run-time modifications to SNOW-17 in operational setting. | on-going | stage 1 | S2LT
4. Generate physically based soil moisture fields.
5. Include variational assimilation of streamflow, precipitation, and potential evapotranspiration into the lumped Sacramento unit hydrograph models for NWSRFS operational implementation.
Hydraulic Models
1. Ice Modeling
a. Develop time series calculator
b. Use time series calculator to test ice jam threshold algorithm
c. Evaluate ice modeling capability in FLDWAV
2. Enhance lock & dam capability in FLDWAV
3. Improve capability to model wind effects
4. Automate FLDWAV calibration procedures
5. Improve efficiency and accuracy of FLDWAV for use within the ensemble system.
| 6. Implement the Simplified Hydraulic Routing Technique (SHRT) in NWSRFS | complete | G2 | ??? | on-going | stage 3 | ???
7. Evaluate COE suite of hydraulic models and other organization’s hydraulic models for their suitability for NWS river forecasting operations.
Reservoir and River Regulation Models
1. Enhance existing NWSRFS models to aid with modeling Streamflow Regulation
| a. Provide a RES-J hindcasting capability | complete | G2 | SAE | complete | G3 | SAE | on-going | stage 4 | SAE
| b. Provide a RES-J LOOKUP3 capability to define a value as a function of two other values. | complete | G2 | SAE | complete | G3 | SAE | on-going | stage 4 | SAE
| i. Applied to a reservoir, the value may be parameterized as a withdrawal or a release from a reservoir. | complete | G2 | SAE | complete | G3 | SAE | on-going | stage 4 | SAE
| ii. Applied to a node, the value may be parameterized as a diversion from the node. | complete | G2 | SAE | complete | G3 | SAE | on-going | stage 4 | SAE
| c. Enhance the RES-J LAGK method to allow the use of variable lags. | complete | G2 | SAE | complete | G3 | SAE | on-going | stage 4 | SAE
| d. Add a POWERGEN (power generation) method to the RES-J operation. | complete | G2 | SAE | on-going | stage 3 | SAE
| i. Enhance the CONS_USE operation to allow the user to specify where return flows re-enter the stream | complete | G2 | SAE | on-going | stage 3 | SAE
| ii. Enhance the CONS_USE operation to allow the user to have the operation compute return flows only, and to do so based on a given diversion time series. | complete | G2 | SAE | on-going | stage 3 | SAE
| iii. Enhance the CONS_USE operation to provide the user the option of specifying the time series from which the diversion will be withdrawn. | complete | G2 | SAE | on-going | stage 3 | SAE
| iv. Enhance the CONS_USE operation to introduce a Mean Areal Precipitation (MAP) input time series in order to account for the demand satisfied by precipitation. | complete | G2 | SAE | on-going | stage 3 | SAE
| v. Enhance the CHANLOSS operation by adding an option to allow the computed loss or gain be a non-linear function of discharge. | complete | G2 | SAE | on-going | stage 3 | SAE
| vi. Enhance the CHANLOSS operation to compute the resulting stream flow after accounting for loss or gain. | complete | G2 | SAE | on-going | stage 3 | SAE
e. Segment Comments –enhance NWSRFS to save comments within the OFS such that punched segments would retain comments for each segment.
f. Multi-valued Time Series Lookup Operation – The Sacramento model includes two multi-value time series containing zone contents and runoff components. The values from these time series may be plotted using PLOT-TS, but the time series cannot otherwise be accessed for manipulation. In some cases, the contents of the zones may provide a useful indicator of basin conditions that could be used to trigger some component of regulation modeling. The LOOKUP3 operation could be enhanced to allow a component of a multi-value time series to be used as the input time series, so that the associated component could be used as a factor in regulation modeling.
g. Integrate NWSRFS Rating Curves – The MAXSTAGE method requires the user to input a rating curve for the downstream node. It is requested that rating curves defined in the system be accessible to this method in place of the rating curve defined in RES‑J. This enhancement will allow the model always uses the most up-to-date rating curve data from NWSRFS database.
h. Improve RES-J Operation Speed – The speed of the RES-J operation has been a major concern in several RFCs. It could really use some improvements to improve efficiency. Below are exerts from previous proposal by RTI. “There are some things that could be done to improve the speed of MAXSTAGE simulations. Most users complaining about speed in the past were not using MAXSTAGE, however, since it didn't work until recently. We recommend that we keep an eye on enhancing performance during the upcoming work and identify level of effort and expected gains for a later proposal.”
2. Develop time series calculator capability
3. Open architecture to allow the use of non-NWSRFS reservoir and river regulation models and easier implementation of new model developments
a. Provide access to USACE/HEC Reservoir Simulation Model in NWSRFS
Architecture
1. Continue the definition and development of a new software architecture and infrastructure to support NWS hydrologic operations.
| a. Create a CHPS software architecture shell (Data Services and Algorithm Services connections) for an example NWSRFS data pre-processor, the MAT. | on-going | stage 2 | SAE
| i. Replace existing MAT science algorithms | on-going | stage 2 | SAE
| ii. Unify MAT computations across NWSRFS | on-going | stage 2 | SAE
| iii. Eliminate the use PPPDB and PPDB fs5file input databases in favor of the IHFS Database for input. | on-going | stage 2 | SAE
| b. Deliver enhanced Frozen Ground Algorithm as part of the AWIPS national baseline, using OHD’s evolving CHPS architecture. | complete | G2 | ??? | in-progress | stage 3 | ???
| c. Create and expand the Hydrology XML Consortium (HydroXC) | on-going |  | SAE
| i. Establish HydroXC | on-going |  | SAE
| ii. Interview and survey all the RFCs about their XML work and future vision | on-going |  | SAE
| iii. Define an XML interface between FLDWAV and FLDVIEW | on-going |  | SAE
| iv. Re-engage consortium members with new data modeling exercises and workshops | on-going |  | SAE
Product Generation and Graphical Dissemination
| 1. Provide enhancements to the HydroGen application | complete | G2 | ??? | on-going | stage 3 | ???
2. Improve XSETS to allow graphical viewing and editing of current and past hydrographs
3. Provide ability for RFC/WFO collaboration on forecast products before public dissemination.
Data Archive
| 1. Provide tools to keep the River Forecast Center (RFC) Archive system (RAX) in sync with the Integrated Hydrologic Forecast System (IHFS) database. | complete | G2 | ??? | on-going | stage 3 | ???
Enhance the existing deterministic verification system
| 1. Add additional metrics, including corresponding graphics, and additional archiving capabilities to the existing verification software. Metrics to be added include the correlation coefficient, forecast variance, observed variance, Gilbert score, and average lead time to detection | complete | G2 | S2LT | complete | G3 | S2LT | on-going | Stage 4 | S2LT
2. Add persistence calculations to verification software
3. Add ability to compute metrics for all physical elements to verification software
| 4. Add ability to compute confidence intervals for metrics to verification software. | complete | G2 | S2LT | on-going | stage 3 | S2LT
5. Identify a path for proper error analysis of deterministic forecasts. This includes work on the operations concept, requirements development, and operational development plan for the “raw model” forecasts.
| a. Add ability to generate “raw model” forecasts to RFS | complete | G2 | S2LT | on-going | stage 3 | S2LT
b. Integrate “raw model” forecast information into the verification system metrics.
6. Investigate new methods to assess trends in the verification data.
a. Propose performance metrics; provide capability to disseminate performance metrics, other results and data; and provide real-time access.
Operational Calibration and Implementation
| 1. Provide support to assist RFCs with operational calibration and implementation | [6 empty] | on-going

## S2LT Det -Distributed
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Hydrometeorological and Climatological Inputs
1. Create hydrometeorological inputs at the appropriate distributed modeling scale.
Hydrologic Forecasting
1. Calibration System Procedures applicable to the distributed modeling scale
a. Develop Simplified Line Search (SLS) automatic calibration procedures
| b. Research and development on usage of SSURGO data to derive a priori model parameters in an effort to improve current SAC-SMA parameter estimation for distributed modeling | on-going | stage 2 | S2LT
| c. Evaluate a parameter regionalization approach for SAC-SMA and SNOW-17 using lumped calibrated parameters, including the use of new sources of validation data such as soil moisture. | on-going | stage 2 | S2LT
d. Evaluate adjusting parameters based on climate indices.
e. Develop Adjoint Based Optimizer (AB-OPT) for unit-hydrograph and SAC-SMA parameters for NWSRFS operational implementation.
2. Hydrologic Forecasting
a. Distributed Model Inter-comparison Project (DMIP)
i. DMIP I (complete)
| 1. Determine if distributed models provide increased simulation accuracy compared to lumped models. (complete) | complete | G2 | S2LT | complete | G3 | S2L2
| 2. Determine what level of model complexity is required to realize improvement in basin outlet simulation. (complete) | complete | G2 | S2LT | complete | G3 | S2L2
| 3. Determine what level of effort is required for distributed model calibration. Determine what improvements are realized compared to non-calibrated and calibrated lumped models. (complete) | complete | G2 | S2LT | complete | G3 | S2L2
| 4. Determine the potential for distributed models set up for basin outlet simulations to generate meaningful hydrographs at interior locations for flash flood forecasting. (complete) | complete | G2 | S2LT | complete | G3 | S2L2
| 5. Determine what characteristics identify a basin as one likely to benefit from distributed modeling versus lumped modeling for basin outlet simulations. Determine if these characteristics can be quantified. (complete) | complete | G2 | S2LT | complete | G3 | S2L2
| 6. Determine how research models behave with forcing data used for operational forecasting. (complete) | complete | G2 | S2LT | complete | G3 | S2L2
| 7. Determine what is the nature and effect of rainfall spatial variability in the DMIP basins. (complete) | complete | G2 | S2LT | complete | G3 | S2L2
ii. DMIP II
| 1. Confirm the results from DMIP 1 with a longer validation period | on-going | stage 1 and 2 | Innovation | ongoing | stage 3 | Innovation
| 2. Expand model comparisons to a Western U.S. basin with significant snow effects. (Compare energy based models with performance of distributed SNOW-17 model) | on-going | stage 1 and 2 | Innovation | ongoing | stage 3 | Innovation
| 3. Expand analysis to include new sources of validation data, particularly use of soil moisture data. | on-going | stage 1 and 2 | Innovation | ongoing | stage 3 | Innovation
| 4. Improve our understanding of uncertainty, in particular the contributions of different model components (inputs, soil moisture accounting, and routing) to overall uncertainty. | on-going | stage 1 and 2 | Innovation | ongoing | stage 3 | Innovation
| 5. Expand comparison to consider forecast mode in addition to simulation mode. | on-going | stage 1 and 2 | Innovation | ongoing | stage 3 | Innovation
b. Hydrology Lab - Research Distributed Hydrologic Model (HL-RDHM)
| i. Initial Development of HL-RDHM: distributed model capabilities using the 4km Hydrologic Rainfall Analysis Project (HRAP) grid as the basic computational element of a basin. In each grid cell, the Sacramento Soil Moisture Accounting model is used to convert rainfall to runoff. Kinematic routing is used in each grid cell and in river channels to move water through the network to the basin outlet. (Complete). The operational capability of this prototype is the Distributed Hydrologic Modeling (DHM) and will be available in OB7. | complete | G2 | S2LT | complete | G3 | S2L2 | on-going | Stage 4 | SAE
ii. Enhance HL-RDHM by including distributed frozen ground modeling capabilities
iii. Enhance HL-RDHM by including distributed snow modeling capabilities including SNOW-17.
iv. Enhance HL-RDHM by including additional routing techniques.
v. Enhance HL-RDHM to include alternative distributed rainfall-runoff techniques.
| vi. Enhance HL-RDHM to include variational streamflow assimilation. | on-going | stage 1 and 2 | S2LT
vii. Create robust parameterization techniques appropriate for the scale of distributed modeling.
viii. Increase spatial resolution of DHM to agree with improved radar spatial resolution
ix. Increase temporal resolution of DHM to agree with improved radar temporal resolution.
c. CONUS Research Model System tests
| i. Evaluation of initial CONUS model for water balance | on-going | stage 2 | S2LT
ii. Develop a strategy for validation: gridded simulations versus point observed data for soil moisture
iii. Data collection: NRCS SCAN, Illinois data for further testing
iv. Test against other soil moisture observations
v. Support OHRFC and CBRFC with RFC-domain runs of HL distributed model
vi. Evaluate initial SAC-SMA and SNOW-17 parameters
vii. Create plans for developing CONUS 4km gridded climatologies for water balance variables.
viii. Add other forcings.
ix. Support NIDIS prototype project in Arizona
Architecture
(See S2LT Probabilistic: Architecture)
Product Generation and Dissemination
1. Develop, generate, and deliver useful information to all customers derived from streamflow forecasts at the distributed modeling element scale
Data Archive
1. Determine data needed to support a verification program of distributed modeling forecast products, support calibration activities and preserve a history of distributed modeling forecasts.
2. Develop national archive and database procedures to collect the data needed.
Verification
1. Research metrics to be used for grid forecast verification.
2. Provide verification of distributed modeling forecast products; provide capability to disseminate verification metrics, other results and data; and provide real-time access

## S2LT Probabilistic
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Hydrometeorological and Climatological Inputs
| 1. Create seamless (1 hr – 365 days) precipitation and temperature ensembles free of climatological noise that include long term climate adjustments. | complete | G2 | S2LT | on-going | Stage 3 | S2LT
| 2. Incorporate the skill of the short-term precipitation (QPF) and temperature (QTF) hydrometeorological forecasts into the ensembles generated with removed noise. | complete | G2 | S2LT | on-going | Stage 3 | S2LT
| 3. Incorporate the skill of the HPC 1-5 day, 6-10 day and 8-14 day hydrometeorological forecasts into the ensembles when QPF/QTF is not available. | complete | G2 | S2LT | on-going | Stage 3 | S2LT
| 4. Develop methods and procedures to quantify the skill relationship seen in the temporal, spatial, and storm type aggregation of forecasts. | complete | G2 | S2LT | on-going | Stage 3 | S2LT
| 5. Create ensembles for the other hydrologic forcing inputs (potential evapotranspiration, freezing heights…) | complete | G2 | S2LT | on-going | Stage 3 | S2LT
| 6. Incorporate the bias and spread corrected hydrologic forcing input ensembles from global and regional climate models using adequate downscaling processes (e.g., frozen GFS) | complete | G2 | S2LT | on-going | Stage 3 | S2LT
7. Develop procedures to ensure smooth transitions between the different ensemble generation procedures.
Hydrologic Forecasting
1. Incorporate real-time data assimilation of hydrologic and hydrometeorological data into operational ensemble prediction.
| a. Develop operations concept and research and development plan for data assimilation | complete | G2 | S2LT | deferred
| b. Develop prototype ensemble data assimilation for RFC short-term ensemble prediction. | complete | G2 | S2LT | deferred
2. Lumped Hydrologic Uncertainty
| a. Evaluate ensemble post-processor | complete | G2 | ??? | Pending Funding
| i. Quantify the significance of the different sources of hydrologic uncertainties (initial condition, calibrated parameter, and structure errors). | complete | G2 | ??? | Pending Funding
| ii. Quantify how well the current post-processor accounts for the uncertainties. | complete | G2 | ??? | Pending Funding
b. Recommend improvements to current post processing system
3. Explicitly determine the uncertainties resulting from the difference between the calibration, real time and forecast forcings.
4. Explicitly Determine the Uncertainty of the Initial Conditions
5. Explicitly Determine the Model Parameters Uncertainty
6. Explicitly Determine the Model Structure Uncertainty
Reservoir and River Regulation Models
1. Explicitly quantify uncertainty in reservoir and river regulation models.
Hydraulic Models
1. Explicitly quantify the hydraulic parameter uncertainty.
a. Derive and test probabilistic channel parameters
Architecture
1. Standardize data management and delivery
2. Develop an architecture management component to control and unite the developments and enhancements of the different ensemble system components to provide a seamless ensemble forecasting system including a migration path for legacy applications.
3. Provide appropriate GUIs to support a seamless system for ensemble forecasting including calibration, ensemble generation, product dissemination and verification.
4. Provide an open architecture to allow the use of non-NWSRFS models and allow for easier implementation of new model developments.
Product Generation and Dissemination
1. Provide low-flow and drought probabilistic products
| a. Non-exceedance Probability Plot (complete) | complete |  | S2LT | complete |  | S2LT | complete |  | S2LT | complete |  | S2LT
| b. Non-exceedance Histogram (complete) | complete |  | S2LT | complete |  | S2LT | complete |  | S2LT | complete |  | S2LT
| c. Provide low flow/stage reference value in ESPADP plots (complete) | complete |  | S2LT | complete |  | S2LT | complete |  | S2LT | complete |  | S2LT
2. Determine what probabilistic information is relevant to users (emergency managers, water managers and general customers)
a. Develop procedures to determine what probabilistic information is relevant to users and the most appropriate ways to communicate the information.
b. Use developed procedures to determine what probabilistic information is relevant to users and the most appropriate ways to communicate the information.
c. Write a report describing the most relevant probabilistic information for users and the most appropriate ways to communicate the information.
d. Implement findings into appropriate GUIs to assist in the ensemble product generation and dissemination.
3. Provide ability to assess and verify ensemble products reliability in real time.
4. Develop appropriate GUI to assist in the ensemble product generation, validation and dissemination.
5. Incorporate more public access to probabilistic products.
6. Provide hydrologic information to other delivery mechanisms (PDAs or other future mobile technologies) from a centralized location as appropriate.
Data Archive
1. Determine data needed to support a verification program of probabilistic products, support calibration activities and preserve a history of probabilistic forecasts.
2. Create a national archive and database procedures to collect the data needed.
Verification
| 1. Provide an ensemble hindcaster capability to allow forecasters and scientists to validate ensemble science, establish a performance envelope of existing and new ensemble capabilities, improve reliability of ensemble forecasts, and assess benefit-cost effectiveness of newly proposed solutions. | complete | G2 | S2LT | on-going | Stage 3 | S2LT
| 2. Develop methods and procedures to verify probabilistic forecasts; provide capability to disseminate verification metrics, other results and data; and provide real-time access to verification metrics | complete | G2 | S2LT | on-going | Stage 3 | S2LT
3. Develop a national performance metric and performance goals to show improvements to probabilistic forecasting.
4. Create an Ensemble Verification Program (EVP) combining the functionality of JProbVS and Ens_verify to verify precipitation and temperature ensembles.
5. Add ability to compute metrics from stored ESPADP tables and observed time series in EVP.
6. Link EVP to the Interactive Verification Program (IVP) to take advantage of all the IVP calculations
7. Add graphics of discrimination, reliability, rank histograms, for fixed locations, time and lead time to EVP.

## S2LT Training
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Short- to Long-Term Training
1. Basic Hydrologic Science - Provide a basic hydrologic science course for RFC forecasters and WFO Hydrologic Program Managers. The course content should include the scientific background to understand and use hydrologic forecasting models. Specific subject matter should include data processing and quality control, hydrologic and hydraulic modeling, and GIS and flood plain mapping.
a. Deliver “Hydrologic Cycle” Module
b. Deliver “Unit Hydrograph Theory” Module
c. Deliver “Streamflow Routing” Module
d. Deliver “Runoff Processes” Module
e. Deliver “Flood Frequency Analysis” Module
f. Deliver “Snowmelt Processes” Module
g. Deliver “Flash Flood Processes” Module
h. Deliver “River Ice” Module
i. Deliver “Long Term Flood Case Study – Rainfall Induced” Module
2. Hydraulic Modeling and Calibration - Provide a hydraulic modeling and calibration course for RFC personnel. The course content should include the necessary skills required to perform hydraulic modeling and calibration.
3. Advanced Hydrologic Sciences - Provide an advanced hydrologic science course for RFC Development and Operations Hydrologists (DOHs), select RFC forecasters and WFO Service Hydrologists. The course content should include the necessary scientific background to understand and implement advances in hydrologic forecasting models. Specific subject matter should include distributed hydrologic modeling, ensemble hydrologic forecasting and precipitation processing.

## Mapping and Graphical
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Graphical E-19s depicting stages for minor, moderate and major flooding
| 1. Proof of concept pilot efforts in North Carolina, Pennsylvania, Kansas, Michigan, Arizona and California. | on-going |  | Graphical Dissemination
2. Working with FEMA to incorporate vendor development of Graphical E-19s into local Floodplain Map Modernization contracts.
3. Write national guidelines for WFOs and RFCs to accomplish implementation of Graphical E-19s.
4. Write technical requirements for FEMA vendors who are developing Graphical E-19s as part of their contracts.
5. National implementation of Graphical E-19 maps through local development and vendor contracts.
Library of static maps
| 1. Proof of concept pilot efforts in a range of areas. | on-going |  | Graphical Dissemination
| 2. Develop a national database inventory of high resolution elevation data and status of FEMA Cooperating Technical Partners Flood Insurance Map Modernization projects at NWS river forecast point locations. | on-going |  | Graphical Dissemination
3. Write national guidelines for WFOs and RFCs to accomplish implementation of a library of static maps.
4. National implementation of a library of static maps through local development and vendor contracts.
Real time maps generated from a simplified routing model
| 1. Produce surface water profiles from the Simplified Hydraulic Routing Technique (SHRT) | complete |  | Graphical Dissemination
2. Produce surface water profiles from the Simplified Dam Break (SMPDBK) model.
3. Develop techniques to merge OHD’s surface water profiles from simplified routing models or steady state hydraulic models to NOS flood inundation maps.
| a. Capability to produce integrated flood inundation maps | on-going |  | Graphical Dissemination
b. Capability to produce salinity forecast
c. Capability to produce temperature/velocity forecasts
| 4. Implement the hardware/software infrastructure necessary to produce flood inundation maps from a simplified routing model or a steady state model integrated in the AWIPS structure. | on-going |  | Graphical Dissemination
5. Provide a flood-forecast mapping application to visually display real time water surface profiles generated from a simplified routing model or a steady state model.
| 6. Provide a generic data interface between FLDVIEW and other flood mapping tools using XML. | on-going |  | Graphical Dissemination
Real time maps generated from a dynamic routing hydraulic model.
| 1. Implement the hardware/software infrastructure necessary to produce flood inundation maps from a dynamic routing hydraulic model integrated in the AWIPS structure. | on-going |  | Graphical Dissemination
| 2. Provide a flood-forecast mapping application to visually display real time water surface profiles generated from a dynamic routing hydraulic model (FLDWAV). | complete |  | Graphical Dissemination | on-going |  | Graphical Dissemination
a. Standard map view (x-y orientation)
b. A cross-section, with the x-axis along the centerline of the stream
c. A cross section that traverses the floodplain from one side to the other.
i. Evaluate accuracy of the flood maps generated using FLDWAV/FLDVIEW in Pennsylvania due to Hurricane Ivan.
ii. Evaluate the accuracy of the maps in the Tar River Basin.
| 3. Provide a generic data interface between FLDVIEW and other flood mapping tools using XML. | on-going |  | Graphical Dissemination
| 4. Merge river hydraulic flood maps with coastal maps. | on-going |  | Graphical Dissemination
5. Automate the procedure of drawing or importing a river centerline using USGS 1:24000 maps, drawing cross sections along a reach, determining elevations along cross sections using ground grids, creating cross-section elevation profiles (FLDXS)
Dissemination
| 1. Evaluate existing dissemination processes | on-going |  | Graphical Dissemination
| 2. Determine products for dissemination | on-going |  | Graphical Dissemination
3. Develop a GIS-based display system to present a variety of hydrologic information to meet the needs of local, regional, and national users.
| a. Evaluate prototype ArcIMS system design | on-going |  | Graphical Dissemination
| i. Incorporate Graphical E-19s with CRH ArcIMS mapping project | on-going |  | Graphical Dissemination
| ii. Convert FLDIMS MapGuide templates for all areas to ArcIMS | on-going |  | Graphical Dissemination
b. Develop Flood Internet Mapping Service (FLDIMS) to overlay flood inundation shape files over geographic data layers showing aerial photographs, roads, structures, and other relevant information.
c. Incorporate census data in this system to enhance hydrologic outlooks, watches, and warnings.
d. Incorporate low flow database information in graphical format utilizing ArcIMS.
e. Provide graphical dissemination of ESPADP digital data, NDFD shapefiles, NWS Doppler radar shapefiles, precipitation data, water supply information, water quality information, and climate data.
3. Provide customer with tools to make their own information sets.
Training
1. GIS Users Workshop - Provide a basic Geographic Information Systems course for RFC forecasters and WFO Hydrologic Program Managers. The course content should include the background to understand and use Geographic Information Systems with regard to hydrology.

## Logistical Verification
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Logistical Verification
| 1. Characterizing point forecasts by service type, frequency and location. | complete | G2 | ??? | on-going | stage 3 | ???
2. Characterizing areal forecasts by service type, frequency and location.
3. Daily queries of the number of issued forecasts by type and location.
4. Quantifying the person effort required to set up a basin for forecasting; including data gathering, calibration, model setup and implementation efforts.
5. Quantifying the person effort required to issue each type of forecast; including manual quality control of input data, forecaster run-time modifications and forecaster review and analysis.
6. Quantifying the timeliness of issued forecasts.

## Outreach
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Outreach
| 1. Develop, produce and distribute Turn Around, Don’t Drown (TADD) national brochure. | complete |  | outreach | complete |  | outreach | complete |  | outreach
| 2. Develop, produce and distribute Floods the Awesome Power national brochure | complete |  | outreach | complete |  | outreach | complete |  | outreach
| 3. Support the development, production and distribution of local outreach brochures. | on-going |  | outreach | on-going |  | outreach | on-going |  | outreach
| 4. Support local outreach activities including Customer Regional Workshops and educational outreach. | on-going |  | outreach | on-going |  | outreach | on-going |  | outreach
| 5. Conduct focus group studies to understand customers needs for and usage of probabilistic streamflow forecasts. | complete |  | outreach | complete |  | outreach | complete |  | outreach | complete |  | outreach
| 6. Conduct biennial Customer Satisfaction Index surveys of AHPS/Hydrologic Services. | on-going |  | outreach | on-going |  | outreach | on-going |  | outreach

## Web Page Deployment
Task Description |  | Development |  |  | Prototype and Validate |  |  | Operational Implemention |  |  | Documention |  |  | Training
|  | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team | Status | HOSIP Gate | Budget Team
Web Page Deployment
| 1. Enhance Web pages by adding new AHPS forecast locations and updating maps | [6 empty] | on-going
2. Implement HydroGen into AWIPS
3. Implement the first phase of the AHPS Products and Information Team recommendations.
| a. Data basing of AHPS web products configuration information | on-going |  | Web Page Deployment | on-going |  | Web Page Deployment | on-going |  | Web Page Deployment
| b. Integrate customer feedback into enhanced river hydrograph | on-going |  | Web Page Deployment | on-going |  | Web Page Deployment | on-going |  | Web Page Deployment
| c. Develop NWS strategy for consistent precipitation graphics. | on-going |  | Web Page Deployment | on-going |  | Web Page Deployment | on-going |  | Web Page Deployment
4. Implement National River Location Database (NRLDB)
| a. Link with local WFO IHFS database to support national database of E-19 information. | on-going | stage 1&2 | ??? | on-going | stage 3 | ???
b. Enhance NRLBB to include services information.
c. Enhance NRLBB to include observational and forecast information to support AHPS web pages.
d. Enhance NRLBB to incorporate graphics files.